## 2019 Bid Sheet (hidden)
2019 HMA SURFACING
Township Projects by Quadrant: SOUTHWEST (Pere Marquette, Summit and Riverton Townships)
|  |  |  | LENGTH | [5 empty] | 22108 | Tons
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | QTY | UNIT | UNIT PRICE | AMOUNT
051 | Pere Marquette | Conrad Road | PM Highway to Meyers Road | 1.03 | HMA Overlay @ 165 #/syd over entire roadway | 1125 | Ton |  |  | 4408 | Tons
052 | PM & Summit | Kinney Rd | PM Highway to Brye | 1.02 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 152 | Ton
053 | Pere Marquette | Orchard Avenue | North Lakeshore Drive to N. Terri Ct | 0.14 | HMA Overlay @ 165 #/syd over entire roadway | 182 | Ton
054 | Pere Marquette | Palmer Blvd & W. Snead Dr. | Chauvez to Snead then End to End on Snead | 0.41 | HMA Overlay @ 165 #/syd over entire roadway | 498 | Ton
055 | Pere Marquette | Russell Street | Washington Avenue to Gary Street | 0.21 | HMA Overlay @ 165 #/syd over entire roadway | 205 | Ton
056 | Pere Marquette | Gary Street | Bryant to Russell | 0.13 | HMA Overlay @ 165 #/syd over entire roadway | 124 | Ton
057 | Pere Marquette | Ellis Street | Russell Street to Eli Street | 0.3 | HMA Overlay @ 165 #/syd over entire roadway | 295 | Ton
058 | Pere Marquette | Lendale, Eli, Lunette | Lendale from Lunette to Ivanhoe, Eli from Ellis to Cul-de-sac, Lunette from Ellis to Lendale | 0.5 | HMA Overlay @ 165 #/syd over entire roadway | 480 | Ton
XXX | Summit | Olmstead Road | East of Lakeshore Drive | 0.04 | From existing HMA Easterly 190' HMA over gravel @ 220#/syd | 47 | Ton
MCRC will need to undercut, place sand, gravel & grade prior to HMA
XXX | Riverton | Hogenson/Bradshaw | From Chauvez Road to New HMA | 0.68 | HMA Leveling @ 165 #/syd over entire roadway | 720 | Ton
XXX | Riverton | Washington Road | Stiles Easterly to Top of Hill | 0.39 | HMA Over Gravel @ 220 #/syd over entire roadway 22' | 580 | Ton
MCRC will need to widen and place 3" of gravel prior to HMA
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. | UNIT | UNIT PRICE |  | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 | 3500 | SYD
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 | 7500 | SYD
[5 empty] | HMA Mix, 0 - 50 Ton | 25 | Ton
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton | 75 | Ton
[5 empty] | HMA Mix, 101 - 200 Ton | 150 | Ton
* HMA 36A Wedging and/or HMA Project SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater | 250 | Ton
2019 HMA SURFACING (Continued)
Township Projects by Quadrant: SOUTHEAST (Custer, Eden, Logan and Branch Townships)
LENGTH
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | QTY | UNIT | UNIT PRICE | AMOUNT
xxx | Branch | Dunbar Road | Between E. Filburn and Hansen | 0.5 | HMA 36A Thin Overlay 22' wide @ 125#/syd. | 410 | Ton |  |  | 942 | Tons
XXX | Branch | East Filburn Road | Taylor Road to Dunbar Road | 0.27 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 140 | Ton
XXX | Branch | Comanche Pass Road | Shoshone to Navajo | 0.23 | HMA LVSP Overlay @ 165 psy at 22' wide | 220 | Ton
XXX | Custer | Conrad Road | Starting at 206 Conrad continuing west for 550' | 0.1 | HMA 36A Wedge, 8'-9' wide w/LG both lanes. | 142 | Ton
XXX | Custer | Wilson Road | starting west of 2888 Wilson Road west for 520' | 0.1 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 30 | Ton
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. | UNIT | UNIT PRICE |  | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 | 3500 | SYD
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 | 7500 | SYD
[5 empty] | HMA Mix, 0 - 50 Ton | 25 | Ton
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton | 75 | Ton
[5 empty] | HMA Mix, 101 - 200 Ton | 150 | Ton
* HMA 36A Wedging and/or HMA Project SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater | 250 | Ton
2019 HMA SURFACING (Continued)
Township Projects by Quadrant: NORTHEAST (Free Soil, Sherman, Sheridan and Meade Townships)
LENGTH
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | QTY | UNIT | UNIT PRICE | AMOUNT
122 | Sheridan | Larson Road | Millerton Road to Fountain Road | 0.98 | HMA LVSP Overlay @ 165 psy at 22' wide | 1045 | Ton |  |  | 3400 | Tons
124 | Sheridan | Larson Road | Starting at the top of the big hill at the end of the ex. HMA then 440' | 0.08 | HMA LVSP Over Aggregate @ 220 psy at 22' wide | 120 | Ton
MCRC will need to widen and add 4" of gravel prior to HMA paving.
121 | Sheridan | Fountain Road | Larson to Schoenher | 0.99 | HMA LVSP Overlay @ 165 psy at 22' wide | 1100 | Ton
xxx | Sheridan | Hughes Road | Fountain Road North for 500' to top of Hill | 0.01 | HMA LVSP Over Aggregate @ 220 psy with Valley Gutter at 28' wide | 200 | Ton
MCRC will need to widen and add 4" of gravel prior to HMA paving.
xxx | Sherman | Fountain Road | Popular Road Easterly to Schoenherr Road | 0.6 | HMA LVSP Overlay @ 165 psy at 22' wide | 645 | Ton
xxx | Sherman | Tuttle Road | Sugar Grove to Dewey Road | 1 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 290 | Ton
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. | UNIT | UNIT PRICE |  | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 | 3500 | SYD
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 | 7500 | SYD
[5 empty] | HMA Mix, 0 - 50 Ton | 25 | Ton
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton | 75 | Ton
[5 empty] | HMA Mix, 101 - 200 Ton | 150 | Ton
* HMA 36A Wedging and/or HMA Project SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater | 250 | Ton
2019 HMA SURFACING (Continued)
Township Projects by Quadrant: NORTHWEST (Hamlin, Amber, Victory and Grant Townships)
LENGTH
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | QTY | UNIT | UNIT PRICE | AMOUNT
xxx | Amber | Conrad Road | Meyers Road east to just past Elk Valley Farms | 2.5 | HMA 36A Wedge, 6'-7' wide, at selected locations. 8' to 9' w/LG for 600' | 652 | Ton |  |  | 1806 | Tons
xxx | Amber | Johnson Rd | E of Stiles Rd from HMA E'ly to past Cemetary | 0.25 | HMA LVSP Over Aggregate @ 220 psy at 28'' wide w/LG | 484 | Ton
xxx | Amber | Johnson Rd | Gordon Road to west of Bridge | 0.27 | HMA LVSP Over Aggregate @ 220 psy at 22' wide | 450 | Ton
MCRC will need to widen and place 5" of gravel prior to HMA
xxx | Hamlin | Piney Ridge Road | M-116 continuing north | 1.5 | HMA 36A Wedge, 6'-7' wide, at selected locations, 1,900' east lane & 2,000' west lane. | 220 | Ton
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. | UNIT | UNIT PRICE |  | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 | 3500 | SYD
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 | 7500 | SYD
[5 empty] | HMA Mix, 0 - 50 Ton | 25 | Ton
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton | 75 | Ton
[5 empty] | HMA Mix, 101 - 200 Ton | 150 | Ton
* HMA 36A Wedging and/or HMA Project SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater | 250 | Ton
2019 HMA SURFACING (Continued)
County Primary Projects |  |  |  | LENGTH
JOB # | TOWNSHIP | ROAD NAME | TERMINI | LENGTH (mi) | ACTIVITY | QTY | UNIT | UNIT PRICE | AMOUNT
1P | Sherman | Sugar Grove Rd | US-31 to Tuttle Road | 2 | HMA Base Crushing and Shaping 6" to 8" deep at 25' wide | 29350 | Syd |  |  | 11552 | Tons | Total | 65 | 750880
[5 empty] | HMA Over Aggregate @ 330 psy (2 lifts) at 24' wide | 4650 | Ton
*Coordination with Mason CRC for adding minimum 3" aggregate on entire roadway. Contractor responsible for initial and final grade shaping.
1P-Alt. | Sherman | Sugar Grove Rd | US-31 to Tuttle Road | 2 | Cold in Place Recycling 5" Depth at 25' wide | 29350 | Syd
[5 empty] | HMA Over Aggregate @ 220 psy at 24' wide | 3100 | Ton
*Coordination with Mason CRC for adding minimum 3" aggregate on entire roadway. Contractor responsible for initial and final grade shaping.
2P | Victory Twp | Sugar Grove Rd | Stiles Road easterly 2.5 miles toward US-31 | 2.5 | HMA LVSP or 5E1, Wedging Over Aggregate Shoulder at 6-7' wide and HMA Overlay @ 165#/Syd @ 12' wide (Est. 800 ton wedge & 2,900 Overlay) | 3700 | Ton |  |  | 3700 | Tons | MDOT | 65 | 240500
[5 empty] | *Optional - Cold-Mill HMA Butt Joints (50' at each end - 1.5" to 0") | 2 | Each
*Coordination with Mason CRC for grading sod & adding aggregate along shoulder as needed.
3P | Amber/Custer | Scottville Road | Johnson Road N. to US-31 | 0.4 | Cold-Milling HMA 1.5" (millings hauled to MCRC yard - 510 E. State Street, Scottville) | 7900 | Syd
[5 empty] | *Optional - Cold-Mill HMA Butt Joints (50' at each end - 2" to 0") | 2 | Each
[5 empty] | HMA LVSP Over Aggregate @ 220 psy at 22' wide | 870 | Ton
4P | Custer | Custer Rd | Chauvez to Hawley | 2 | HMA LVSP Overlay @ 170 #/syd at 22' wide | 2200 | Ton
[5 empty] | *Optional - Cold-Mill HMA Butt Joints (50' at each end - 1.5" to 0") | 2 | Each
5P | Sherman | US-31 (NB) | 220' N of Beyer Rd. CL continuing S. for 4,200 Lft (12' wide) | 0.795 | Cold-Milling HMA 1.5" (millings hauled to MCRC yard - 510 E. State Street, Scottville) | 5600 | Syd
[5 empty] | HMA 5E3 Overlay @ 170 #/syd | 476 | Ton |  |  | 476 | Tons | MDOT | 65 | 30940
6P | Freesoil | US-31 (SB) | S. of Townline then North 5,000 Lft just S of Freeman (12' wide) | 0.95 | Cold-Milling HMA 1.5" (millings hauled to MCRC yard - 510 E. State Street, Scottville) | 6667 | Syd
[5 empty] | HMA 5E3 Overlay @ 170 #/syd | 566 | Ton |  |  | 566 | Tons | MDOT | 65 | 36790
7P* | Custer | Custer Rd | Conrad to Wilson Road | 1 | HMA 36A Wedge, 8'-9' wide w/LG, at selected locations, both lanes. | 600 | Ton
8P* | Summit | S. Lakeshore Dr | Consumers Power Bridge N. 600' | 0.12 | HMA 36A Wedge, 12'-13' wide w/LG, both lanes. | 140 | Ton
9P* | Pere Marquette | Rasmussen | Jebavy Drive E. 2,500' | 0.48 | HMA 36A Wedge, 6'-7' wide, at selected locations, both lanes. | 120 | Ton
10P* | Riverton | Hawley Road | 1/4 mile W of Morton E. to Stiles | 1.25 | HMA 36A Wedge, 6'-7' wide, at selected locations, both lanes. | 300 | Ton
11P* | Riverton | Chauvez | 1/4 mile W. of Hogenson to 1/4 mile E. of Hogenson | 0.5 | HMA 36A Wedge, 6'-7' wide, at selected locations, both lanes. | 130 | Ton
[10 empty] | 6810 | Tons | MCRC | 65 | 442650
[5 empty] | ACTIVITY / TONNAGE BY SITE | UNIT |  | UNIT PRICE | AMOUNT
[5 empty] | HMA Base Crushing and Shaping 2,500 to 5,000 | 3500 | SYD
[5 empty] | HMA Base Crushing and Shaping 5,000 to 10,000 | 7500 | SYD
[5 empty] | HMA Mix, 0 - 50 Ton | 25 | Ton
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton | 75 | Ton
[5 empty] | HMA Mix, 101 - 200 Ton | 150 | Ton
[5 empty] | HMA Mix, 201 Ton and Greater | 250 | Ton
* HMA 36A Wedging and/or HMA Project SHALL be completed on or before August 1, 2019

## 2019 Bid Award (hidden)
2019 HMA SURFACING |  |  |  |  | UPDATED 5/20/2019 | 23475 | Tons
Township Projects by Quadrant: SOUTHWEST (Pere Marquette, Summit and Riverton Townships)
|  |  |  | LENGTH |  |  |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
051 | Pere Marquette | Conrad Road | PM Highway to Meyers Road | 1.03 | HMA Overlay @ 165 #/syd over entire roadway | 1125 | Ton | 65 | 73125 | 61.99 | 69738.75
052** | PM & Summit | Kinney Rd | PM Highway to Brye | 1.02 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 152 | Ton | 100 | 15200 | 80.44 | 12226.88
053 | Pere Marquette | Orchard Avenue | North Lakeshore Drive to N. Terri Ct | 0.14 | HMA Overlay @ 165 #/syd over entire roadway | 182 | Ton | 100 | 18200 | 84.81 | 15435.42
054 | Pere Marquette | Palmer Blvd & W. Snead Dr. | Chauvez to Snead then End to End on Snead | 0.41 | HMA Overlay @ 165 #/syd over entire roadway | 498 | Ton | 80 | 39840 | 73.07 | 36388.86
055 | Pere Marquette | Russell Street | Washington Avenue to Ellis Street | 0.21 | HMA Overlay @ 165 #/syd over entire roadway | 205 | Ton | 80 | 16400 | 72.59 | 14880.95
056 | Pere Marquette | Gary Street | Bryant to Russell | 0.13 | HMA Overlay @ 165 #/syd over entire roadway | 124 | Ton | 100 | 12400 | 74.46 | 9233.04
057 | Pere Marquette | Ellis Street | Bryant Street to Eli Street | 0.3 | HMA Overlay @ 165 #/syd over entire roadway | 300 | Ton | 80 | 24000 | 72.01 | 21603
058 | Pere Marquette | Lendale, Eli, Lunette | Lendale from Lunette to Ivanhoe, Eli from Ellis to Cul-de-sac, Lunette from Ellis to Lendale | 0.5 | HMA Overlay @ 165 #/syd over entire roadway | 480 | Ton | 80 | 38400 | 75.18 | 36086.4
014 | Summit | Olmstead Road | East of Lakeshore Drive | 0.04 | From existing HMA Easterly 190' HMA over gravel @ 220#/syd | 53 | Ton | 200 | 10600 | 112.05 | 5938.65
MCRC will need to undercut, place sand, gravel & grade prior to HMA
021 | Riverton | Hogenson/Bradshaw | From Chauvez Road to New HMA | 0.68 | HMA Leveling @ 165 #/syd over entire roadway | 720 | Ton | 70 | 50400 | 68.5 | 49320
XXX | Riverton | Washington Road | Stiles Easterly to Top of Hill | 0.39 | HMA Over Gravel @ 220 #/syd over entire roadway 22' | 580 | Ton | 70 | 40600 | 68.5 | 39730
MCRC will need to widen and place 3" of gravel prior to HMA
[6 empty] | 3839 | Ton | Subtotal | 298565 | Subtotal | 270851.95
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. | UNIT | UNIT PRICE | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton | 75 | Ton | 150 | 11250 | 140 | 10500
** HMA 36A Wedging SHALL be completed on or before June 19, 2019 |  |  |  |  | HMA Mix, 101 - 200 Ton | 150 | Ton | 100 | 15000 | 95 | 14250
* HMA 36A Wedging Projects SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 28, 2019 | [7 empty] | Subtotal | 71250 | Subtotal | 70800
2019 HMA SURFACING (Continued) |  |  |  |  | UPDATED 5/20/2019
Township Projects by Quadrant: SOUTHEAST (Custer, Eden, Logan and Branch Townships)
|  |  |  | LENGTH |  |  |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
081 | Branch | East Filburn Road | Taylor Road to Dunbar Road | 0.27 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 130 | Ton | 100 | 13000 | 86.53 | 11248.9
082 | Branch | Campbell Road | Between Johnson Road & Hansen Road (East Lane) | 0.3 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 108 | Ton | 100 | 10800 | 95 | 10260
083 | Branch | Dunbar Road | Between E. Filburn and Hansen | 0.5 | HMA LVSP Overlay @ 165 psy at 22' wide | 520 | Ton | 80 | 41600 | 77.81 | 40461.2
084 | Branch | Comanche Pass Road | Shoshone to Navajo | 0.23 | HMA LVSP Overlay @ 165 psy at 22' wide | 220 | Ton | 80 | 17600 | 77.81 | 17118.2
072 | Custer | Conrad Road | Starting at 206 Conrad continuing west for 550' | 0.1 | HMA 36A Wedge, 8'-9' wide w/LG both lanes. | 142 | Ton | 100 | 14200 | 85.61 | 12156.62
074 | Custer | Wilson Road | starting west of 2888 Wilson Road west for 520' | 0.1 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 30 | Ton | 200 | 6000 | 135 | 4050
[6 empty] | 1150 | Ton | Subtotal | 103200 | Subtotal | 95294.92
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. | UNIT | UNIT PRICE | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton | 75 | Ton | 150 | 11250 | 140 | 10500
[5 empty] | HMA Mix, 101 - 200 Ton | 150 | Ton | 100 | 15000 | 95 | 14250
* HMA 36A Wedging Projects SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 28, 2019 | [7 empty] | Subtotal | 71250 | Subtotal | 70800
2019 HMA SURFACING (Continued) |  |  |  |  | UPDATED 5/20/2019
Township Projects by Quadrant: NORTHEAST (Free Soil, Sherman, Sheridan and Meade Townships)
|  |  |  | LENGTH |  |  |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
122 | Sheridan | Larson Road | Millerton Road to Fountain Road | 0.98 | HMA LVSP Overlay @ 165 psy at 22' wide | 1045 | Ton | 65 | 67925 | 66.42 | 69408.9
124 | Sheridan | Larson Road | Starting at the top of the big hill at the end of the ex. HMA then 440' | 0.08 | HMA LVSP Over Aggregate @ 220 psy at 22' wide | 120 | Ton | 100 | 12000 | 66.42 | 7970.4
MCRC will need to widen and add 4" of gravel prior to HMA paving.
121 | Sheridan | Fountain Road | Larson to Schoenher | 0.99 | HMA LVSP Overlay @ 165 psy at 22' wide | 1100 | Ton | 65 | 71500 | 64.69 | 71159
xxx | Sheridan | Hughes Road | Fountain Road North for 500' to top of Hill | 0.01 | HMA LVSP Over Aggregate @ 220 psy with Valley Gutter at 28' wide | 200 | Ton | 100 | 20000 | 83.02 | 16604
MCRC will need to widen and add 4" of gravel prior to HMA paving.
113 | Sherman | Fountain Road | From Sawmill Drive Easterly to Schoenherr Road | 0.54 | HMA LVSP Overlay @ 165 psy at 22' wide | 570 | Ton | 70 | 39900 | 64.69 | 36873.3
xxx | Sherman | Tuttle Road | Sugar Grove to Dewey Road | 1 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 290 | Ton | 80 | 23200 | 75.81 | 21984.9
[6 empty] | 2835 | Ton | Subtotal | 123400 | Subtotal | 116002.7
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. | UNIT | UNIT PRICE | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton | 75 | Ton | 150 | 11250 | 140 | 10500
[5 empty] | HMA Mix, 101 - 200 Ton | 150 | Ton | 100 | 15000 | 95 | 14250
* HMA 36A Wedging Projects SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 28, 2019 | [7 empty] | Subtotal | 71250 | Subtotal | 70800
2019 HMA SURFACING (Continued) |  |  |  |  | UPDATED 5/20/2019
Township Projects by Quadrant: NORTHWEST (Hamlin, Amber, Victory and Grant Townships)
|  |  |  | LENGTH |  |  |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
066 | Amber | Conrad Road | Meyers Road east to just past Elk Valley Farms | 2.5 | HMA 36A Wedge, 6'-7' wide, at selected locations. 8' to 9' w/LG for 600' | 652 | Ton | 70 | 45640 | 67.97 | 44316.44
069 | Amber | Johnson Rd | E of Stiles Rd from HMA E'ly to past Cemetary | 0.25 | HMA LVSP Over Aggregate @ 220 psy at 28'' wide w/LG | 484 | Ton | 80 | 38720 | 63.29 | 30632.36
064 | Amber | Johnson Rd | Gordon Road to west to Bridge | 0.27 | HMA LVSP Over Aggregate @ 220 psy at 22' wide | 450 | Ton | 80 | 36000 | 63.29 | 28480.5
MCRC will need to widen and place 5" of gravel prior to HMA
099B | Hamlin | Rath Road | Jagger Road north 800' | 0.15 | HMA LVSP Over Aggregate @ 220 psy at 22' wide | 216 | Ton | 80 | 17280 | 90 | 19440
094 | Hamlin | Piney Ridge Road | M-116 continuing north | 1.5 | HMA 36A Wedge, 6'-7' wide, at selected locations, 1,900' east lane & 2,000' west lane. | 220 | Ton | 80 | 17600 | 84 | 18480
[6 empty] | 1538 | Ton | Subtotal | 116520 | Subtotal | 110716.94
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. | UNIT | UNIT PRICE | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton | 75 | Ton | 150 | 11250 | 140 | 10500
[5 empty] | HMA Mix, 101 - 200 Ton | 150 | Ton | 100 | 15000 | 95 | 14250
* HMA 36A Wedging Projects SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 28, 2019 | [7 empty] | Subtotal | 71250 | Subtotal | 70800
2019 HMA SURFACING (Continued) |  |  |  |  | UPDATED 5/20/2019
County Primary Projects |  |  |  | LENGTH |  |  |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION
JOB # | TOWNSHIP | ROAD NAME | TERMINI | LENGTH (mi) | ACTIVITY | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
1P | Sherman | Sugar Grove Rd | US-31 to Tuttle Road | 2 | HMA Base Crushing and Shaping 6" to 8" deep at 25' wide | 29350 | Syd | 1.2 | 35220 | 0.85 | 24947.5
|  |  | HOLD - MCRC NEEDS TO INSTALL CULVERTS |  | HMA Over Aggregate @ 330 psy (2 lifts) at 24' wide | 4650 | Ton | 65 | 302250 | 59.36 | 276024
*Coordination with Mason CRC for adding minimum 3" aggregate on entire roadway & culvert replacements. Contractor responsible for initial and final grade shaping.
1P-Alt. | Sherman | Sugar Grove Rd | US-31 to Tuttle Road | 2 | Cold in Place Recycling 5" Depth at 25' wide | 29350 | Syd | 8.5 | 249475
[5 empty] | HMA Over Aggregate @ 220 psy at 24' wide | 3100 | Ton | 65 | 201500 | 59.36 | 184016
*Coordination with Mason CRC for adding minimum 3" aggregate on entire roadway. Contractor responsible for initial and final grade shaping.
2P | Victory Twp | Sugar Grove Rd | Stiles Road easterly 2.5 miles toward US-31 | 2.5 | HMA LVSP or 5E1, Wedging Over Aggregate Shoulder at 6-7' wide and HMA Overlay @ 165#/Syd @ 12' wide (Est. 800 ton wedge & 2,900 Overlay) | 3700 | Ton | 65 | 240500 | 59.36 | 219632
[5 empty] | *Optional - Cold-Mill HMA Butt Joints (50' at each end - 1.5" to 0") | 2 | Each | 1500 | 3000 | 1740 | 3480
*Coordination with Mason CRC for grading sod & adding aggregate along shoulder as needed.
3P | Amber/Custer | Scottville Road | Johnson Road N. to US-31 | 0.4 | Cold-Milling HMA 1.5" (millings hauled to MCRC yard - 510 E. State Street, Scottville) | 7900 | Syd | 2 | 15800 | 1.2 | 9480
[5 empty] | *Optional - Cold-Mill HMA Butt Joints (50' at each end - 2" to 0") | 2 | Each | 1500 | 3000 | 1740 | 3480
[5 empty] | HMA LVSP Overlay @ 220 psy at 22' wide | 870 | Ton | 70 | 60900 | 66.31 | 57689.7
4P | Custer | Custer Rd | Chauvez to Hawley | 2 | HMA LVSP Overlay @ 170 #/syd at 22' wide | 2200 | Ton | 65 | 143000 | 62.9 | 138380
[5 empty] | *Optional - Cold-Mill HMA Butt Joints (50' at each end - 1.5" to 0") | 2 | Each | 1500 | 3000 | 1740 | 3480
5P | Sherman | US-31 (NB) | 220' N of Beyer Rd. CL continuing S. for 4,200 Lft (12' wide) | 0.795 | Cold-Milling HMA 1.5" (millings hauled to MCRC yard - 510 E. State Street, Scottville) | 5600 | Syd | 2 | 11200 | 1.24 | 6944
[5 empty] | HMA 5E3 Overlay @ 170 #/syd | 476 | Ton | 80 | 38080 | 72.75 | 34629
6P | Freesoil | US-31 (SB) | S. of Townline then North 5,000 Lft just S of Freeman (12' wide) | 0.95 | Cold-Milling HMA 1.5" (millings hauled to MCRC yard - 510 E. State Street, Scottville) | 6667 | Syd | 2 | 13334 | 1.27 | 8467.09
[5 empty] | HMA 5E3 Overlay @ 170 #/syd | 566 | Ton | 70 | 39620 | 71.75 | 40610.5
7P* | Custer | Custer Rd | Conrad to Wilson Road | 1 | HMA 36A Wedge, 8'-9' wide w/LG, at selected locations, both lanes. | 600 | Ton | 70 | 42000 | 69.07 | 41442
8P* | Summit | S. Lakeshore Dr | Consumers Power Bridge N. 600' | 0.12 | HMA 36A Wedge, 12'-13' wide w/LG, both lanes. | 140 | Ton | 100 | 14000 | 90 | 12600
9P* | Pere Marquette | Rasmussen | Jebavy Drive E. 2,500' | 0.48 | HMA 36A Wedge, 6'-7' wide, at selected locations, both lanes. | 120 | Ton | 100 | 12000 | 93 | 11160
10P* | Riverton | Hawley Road | 1/4 mile W of Morton E. to Stiles | 1.25 | HMA 36A Wedge, 6'-7' wide, at selected locations, both lanes. | 300 | Ton | 80 | 24000 | 84 | 25200
11P* | Riverton | Chauvez | 1/4 mile W. of Hogenson to 1/4 mile E. of Hogenson | 0.5 | HMA 36A Wedge, 6'-7' wide, at selected locations, both lanes. | 130 | Ton | 100 | 13000 | 93 | 12090
12P** | Grant | Townline & Quarterline | Stiles to Quarterline & Townline to Countyline | 7.3 | HMA 36A Wedge, 11.5' wide, at selected locations, both lanes. | 235 | Ton | 80 | 18800 | 90 | 21150
13P | Summit | Lakeshore Drive | Between Washington & Sunset Lane | 0.12 | HMA LVSP Overlay @ 165 #/syd at 22' wide | 126 | Ton | 100 | 12600 | 95 | 11970
[6 empty] | 14113 | Ton | Subtotal | 1045304 | Subtotal | 962855.79
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. | UNIT | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
[5 empty] | HMA Base Crushing and Shaping 2,500 to 5,000 | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
[5 empty] | HMA Base Crushing and Shaping 5,000 to 10,000 | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton | 75 | Ton | 150 | 11250 | 140 | 10500
** HMA 36A Wedging SHALL be completed on or before June 15, 2019 |  |  |  |  | HMA Mix, 101 - 200 Ton | 150 | Ton | 100 | 15000 | 95 | 14250
* HMA 36A Wedging Projects SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 28, 2019 | [7 empty] | Subtotal | 71250 | Subtotal | 70800
UPDATED 5/20/2019
|  |  | 2019 HMA SURFACING - BID SUMMARY PER QUADRANT |  |  |  |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION
[5 empty] | Township Projects by Quadrant: SOUTHWEST (Pere Marquette, Summit and Riverton Townships) |  |  |  | 298565 |  | 270851.95
[5 empty] | Township Projects by Quadrant: SOUTHEAST (Custer, Eden, Logan and Branch Townships) |  |  |  | 103200 |  | 95294.92
[5 empty] | Township Projects by Quadrant: NORTHEAST (Free Soil, Sherman, Sheridan and Meade Townships) |  |  |  | 123400 |  | 116002.7
[5 empty] | Township Projects by Quadrant: NORTHWEST (Hamlin, Amber, Victory and Grant Townships) |  |  |  | 116520 |  | 110716.94
[5 empty] | County Primary Projects |  |  |  | 1045304 |  | 962855.79 | STR#
[8 empty] | TOTAL AMOUNT | 1686989 | TOTAL AMOUNT | 1555722.3 | 3.66
3.79
REVISIONS
2019-03-08
2019-04-22
2019-04-25
2019-05-20
[5 empty] | HMA Mix, 0 - 50 Ton | 200 |  |  |  | Total Primary | 962855.79
[5 empty] | HMA Mix, 51 - 100 Ton | 150 |  |  |  | MDOT Primary | -130000
[5 empty] | HMA Mix, 101 - 200 Ton | 100 |  |  |  | MDOT Primary | -250000
[5 empty] | HMA Mix, 201 - 500 Ton | 80 |  |  |  | MCRC Primary | 582855.79
[5 empty] | HMA Mix, 501 - 1000 Ton | 70
[5 empty] | HMA Mix, 1000+ Ton | 65

## 2020 Remaining Work (hidden)
[8 empty] | Total |  | Remaining | Primary | Townships
2019 HMA SURFACING |  |  |  |  | UPDATED 11/11/2019 |  |  | 24065 | Tons | 5836 | 4680 | 1156
Township Projects by Quadrant: SOUTHWEST (Pere Marquette, Summit and Riverton Townships)
|  |  |  | LENGTH |  |  | Actual | PLAN |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION |  |  | Actual | Actual
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT |  | AMOUNT | Percent
051 | Pere Marquette | Conrad Road | PM Highway to Meyers Road | 1.03 | HMA Overlay @ 165 #/syd over entire roadway | 2019-07-17 | 1061.39 | 1125 | Ton | 65 | 73125 | 61.99 | 69738.75 |  | 65795.5661 | 94.35%
052** | PM & Summit | Kinney Rd | PM Highway to Brye | 1.02 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 2019-07-08 | 144.6 | 152 | Ton | 100 | 15200 | 80.44 | 12226.88 |  | 11631.624 | 95.13%
053 | Pere Marquette | Orchard Avenue | North Lakeshore Drive to N. Terri Ct | 0.14 | HMA Overlay @ 165 #/syd over entire roadway | 2019-08-28 | 212 | 182 | Ton | 100 | 18200 | 84.81 | 15435.42 |  | 17979.72 | 116.5%
054 | Pere Marquette | Palmer Blvd & W. Snead Dr. | Chauvez to Snead then End to End on Snead | 0.41 | HMA Overlay @ 165 #/syd over entire roadway | 2019-08-28 | 538.32 | 498 | Ton | 80 | 39840 | 73.07 | 36388.86 |  | 39335.0424 | 108.1%
055 | Pere Marquette | Russell Street | Washington Avenue to Ellis Street | 0.21 | HMA Overlay @ 165 #/syd over entire roadway | 2019-07-12 | 207.38 | 205 | Ton | 80 | 16400 | 72.59 | 14880.95 |  | 15053.7142 | 101.2%
056 | Pere Marquette | Gary Street | Bryant to Russell | 0.13 | HMA Overlay @ 165 #/syd over entire roadway | 2019-07-12 | 130.25 | 124 | Ton | 100 | 12400 | 74.46 | 9233.04 |  | 9698.415 | 105%
057 | Pere Marquette | Ellis Street | Bryant Street to Eli Street | 0.3 | HMA Overlay @ 165 #/syd over entire roadway | 2019-07-12 | 201.46 | 295 | Ton | 80 | 23600 | 72.01 | 21242.95 |  | 14507.1346 | 68.29%
058 | Pere Marquette | Lendale, Eli, Lunette | Lendale from Lunette to Ivanhoe, Eli from Ellis to Cul-de-sac, Lunette from Ellis to Lendale | 0.5 | HMA Overlay @ 165 #/syd over entire roadway | 7/12/2019 & 7/15/2019 | 489.08 | 480 | Ton | 80 | 38400 | 75.18 | 36086.4 |  | 36769.0344 | 101.9%
014 | Summit | Olmstead Road | East of Lakeshore Drive | 0.04 | From existing HMA Easterly 190' HMA over gravel @ 220#/syd | 2019-08-29 | 50.74 | 53 | Ton | 200 | 10600 | 112.05 | 5938.65 |  | 5685.417 | 95.74%
MCRC will need to undercut, place sand, gravel & grade prior to HMA
021 | Riverton | Hogenson/Bradshaw | From Chauvez Road to New HMA | 0.68 | HMA Leveling @ 165 #/syd over entire roadway | 2019-07-13 | 692.94 | 720 | Ton | 70 | 50400 | 68.5 | 49320 |  | 47466.39 | 96.24%
XXX | Riverton | Washington Road | Stiles Easterly to Top of Hill | 0.39 | HMA Over Gravel @ 220 #/syd over entire roadway 22' |  |  | 580 | Ton | 70 | 40600 | 68.5 | 39730
MCRC will need to widen and place 3" of gravel prior to HMA
[7 empty] | 3728.16 | 3834 | Ton | Subtotal | 298165 | Subtotal | 270491.9 |  | 263922.0577 | 97.57%
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | UNIT | UNIT PRICE | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 150 | 11250 | 140 | 10500
** HMA 36A Wedging SHALL be completed on or before June 15, 2019 |  |  |  |  | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 100 | 15000 | 95 | 14250
* HMA 36A Wedging Projects SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 28, 2019 | [9 empty] | Subtotal | 71250 | Subtotal | 70800
2019 HMA SURFACING (Continued) |  |  |  |  | UPDATED 11/11/2019
Township Projects by Quadrant: SOUTHEAST (Custer, Eden, Logan and Branch Townships)
|  |  |  | LENGTH |  |  | Actual | PLAN |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION |  |  | Actual | Actual
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT |  | AMOUNT | Percent
081 | Branch | East Filburn Road | Taylor Road to Dunbar Road | 0.27 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 2019-08-27 | 154.33 | 130 | Ton | 100 | 13000 | 86.53 | 11248.9 |  | 13354.1749 | 118.7%
082 | Branch | Campbell Road | Between Johnson Road & Hansen Road (East Lane) | 0.3 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 2019-08-27 | 140.61 | 108 | Ton | 100 | 10800 | 95 | 10260 |  | 13357.95 | 130.2%
083 | Branch | Dunbar Road | Between E. Filburn and Hansen | 0.5 | HMA LVSP Overlay @ 165 psy at 22' wide | 2019-08-27 | 500 | 520 | Ton | 80 | 41600 | 77.81 | 40461.2 |  | 38905 | 96.15%
084 | Branch | Comanche Pass Road | Shoshone to Navajo | 0.23 | HMA LVSP Overlay @ 165 psy at 22' wide | 2019-08-27 | 237.02 | 220 | Ton | 80 | 17600 | 77.81 | 17118.2 |  | 18442.5262 | 107.7%
072 | Custer | Conrad Road | Starting at 206 Conrad continuing west for 550' | 0.1 | HMA 36A Wedge, 8'-9' wide w/LG both lanes. | 2019-07-22 | 150.33 | 142 | Ton | 100 | 14200 | 85.61 | 12156.62 |  | 12869.7513 | 105.9%
074 | Custer | Wilson Road | starting west of 2888 Wilson Road west for 520' | 0.1 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 2019-08-28 | 27 | 30 | Ton | 200 | 6000 | 135 | 4050 |  | 3645 | 90%
[7 empty] | 1209.29 | 1150 | Ton | Subtotal | 103200 | Subtotal | 95294.92 |  | 100574.4024 | 105.5%
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | UNIT | UNIT PRICE | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 150 | 11250 | 140 | 10500
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 100 | 15000 | 95 | 14250
* HMA 36A Wedging Projects SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 28, 2019 | [9 empty] | Subtotal | 71250 | Subtotal | 70800
2019 HMA SURFACING (Continued) |  |  |  |  | UPDATED 11/11/2019
Township Projects by Quadrant: NORTHEAST (Free Soil, Sherman, Sheridan and Meade Townships)
|  |  |  | LENGTH |  |  | Actual | PLAN |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION |  |  | Actual | Actual
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT |  | AMOUNT | Percent
122 | Sheridan | Larson Road | Millerton Road to Fountain Road | 0.98 | HMA LVSP Overlay @ 165 psy at 22' wide | 2019-06-26 | 1188.75 | 1045 | Ton | 65 | 67925 | 66.42 | 69408.9 |  | 78956.775 | 113.8%
124 | Sheridan | Larson Road | Starting at the top of the big hill at the end of the ex. HMA then 440' | 0.08 | HMA LVSP Over Aggregate @ 220 psy at 22' wide | 2019-07-19 | 135.2 | 120 | Ton | 100 | 12000 | 66.42 | 7970.4 |  | 8979.984 | 112.7%
MCRC will need to widen and add 4" of gravel prior to HMA paving.
121 | Sheridan | Fountain Road | Larson to Schoenher | 0.99 | HMA LVSP Overlay @ 165 psy at 22' wide | 6/3 & 6/26 | 1101.95 | 1100 | Ton | 65 | 71500 | 64.69 | 71159 |  | 71285.1455 | 100.2%
xxx | Sheridan | Hughes Road | Fountain Road North for 500' to top of Hill | 0.01 | HMA LVSP Over Aggregate @ 220 psy with Valley Gutter at 28' wide |  |  | 200 | Ton | 100 | 20000 | 83.02 | 16604
MCRC will need to widen and add 4" of gravel prior to HMA paving.
113 | Sherman | Fountain Road | From Sawmill Drive Easterly to Schoenherr Road | 0.54 | HMA LVSP Overlay @ 165 psy at 22' wide | 2019-06-03 | 570 | 570 | Ton | 70 | 39900 | 64.69 | 36873.3 |  | 36873.3 | 100%
xxx | Sherman | Tuttle Road | Sugar Grove to Dewey Road | 1 | HMA 36A Wedge, 6'-7' wide, at selected locations. |  |  | 290 | Ton | 80 | 23200 | 75.81 | 21984.9
127 | Sheridan | Dewey Road | Between Morse & Benson Road | 0.04 | HMA Patch, wedge & overlay 22' wide by 200' long (bridge repair) | 2019-07-19 | 54.28 | 55 | Ton | 150 | 8250 | 140 | 7700 |  | 7599.2 | 98.69%
[7 empty] | 3050.18 | 2890 | Ton | Subtotal | 131650 | Subtotal | 123702.7 |  | 124737.6295 | 100.8%
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | UNIT | UNIT PRICE | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 150 | 11250 | 140 | 10500
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 100 | 15000 | 95 | 14250
* HMA 36A Wedging Projects SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 28, 2019 | [9 empty] | Subtotal | 71250 | Subtotal | 70800
2019 HMA SURFACING (Continued) |  |  |  |  | UPDATED 11/11/2019
Township Projects by Quadrant: NORTHWEST (Hamlin, Amber, Victory and Grant Townships)
|  |  |  | LENGTH |  |  | Actual | PLAN |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION |  |  | Actual | Actual
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT |  | AMOUNT | Percent
066 | Amber | Conrad Road | Meyers Road east to just past Elk Valley Farms | 2.5 | HMA 36A Wedge, 6'-7' wide, at selected locations. 8' to 9' w/LG for 600' | 2019-07-29 | 639.08 | 652 | Ton | 70 | 45640 | 67.97 | 44316.44 |  | 43438.2676 | 98.02%
|  |  | Still about 60 tons of wedging to complete in 2020 |  | Conrad & Meyers (Patch) | 2019-09-06 | 75
069 | Amber | Johnson Rd | E of Stiles Rd from HMA E'ly to past Cemetary | 0.25 | HMA LVSP Over Aggregate @ 220 psy at 28'' wide w/LG |  |  | 484 | Ton | 80 | 38720 | 63.29 | 30632.36
064 | Amber | Johnson Rd | Gordon Road to west to Bridge | 0.27 | HMA LVSP Over Aggregate @ 220 psy at 22' wide | 2019-10-29 | 460.79 | 450 | Ton | 80 | 36000 | 63.29 | 28480.5 |  | 29163.3991 | 102.4%
MCRC will need to widen and place 5" of gravel prior to HMA
099B | Hamlin | Rath Road | Jagger Road north 800' | 0.15 | HMA LVSP Over Aggregate @ 220 psy at 22' wide | 2020 |  | 216 | Ton | 80 | 17280 | 90 | 19440 |  | 0 | 0%
094 | Hamlin | Piney Ridge Road | M-116 continuing north | 1.5 | HMA 36A Wedge, 6'-7' wide, at selected locations, 1,900' east lane & 2,000' west lane. | 2020 |  | 220 | Ton | 80 | 17600 | 84 | 18480 |  | 0 | 0%
132 | Grant | Morton Road | Countyline Road south to Sass Road | 0.5 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 2020 |  | 260 | Ton | 80 | 20800 | 90 | 23400 |  | 0 | 0%
[7 empty] | 1174.87 | 1798 | Ton | Subtotal | 137320 | Subtotal | 134116.94 |  | 72601.6667 | 54.13%
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | UNIT | UNIT PRICE | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 150 | 11250 | 140 | 10500
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 100 | 15000 | 95 | 14250
* HMA 36A Wedging Projects SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 28, 2019 | [9 empty] | Subtotal | 71250 | Subtotal | 70800
2019 HMA SURFACING (Continued) |  |  |  |  | UPDATED 11/11/2019
County Primary Projects |  |  |  | LENGTH |  |  | Actual | PLAN |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION |  |  | Actual | Actual
JOB # | TOWNSHIP | ROAD NAME | TERMINI | LENGTH (mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT |  | AMOUNT | Percent
1P | Sherman | Sugar Grove Rd | US-31 to Tuttle Road | 2 | HMA Over Aggregate @ 330 psy (2 lifts) at 24' wide |  |  | 29350 | Syd | 1.2 | 35220 | 0.85 | 24947.5
[5 empty] | HMA LVSP or 5E1, Wedging Over Aggregate Shoulder at 8' wide and HMA Overlay @ 165#/Syd @ 24-28' wide (Est. 1,100 ton wedge & 2,710 Overlay) | 2020 |  | 3810 | Ton | 65 | 247650 | 59.36 | 226161.6 |  | 0 | 0%
[5 empty] | *Coordination with Mason CRC for adding minimum 3" aggregate on entire roadway & culvert replacements. Contractor responsible for initial and final grade shaping. | 2020 |  | 1 | Each | 1500 | 1500 | 1740 | 1740 |  | 0 | 0%
1P-Alt. | Sherman | Sugar Grove Rd | US-31 to Tuttle Road | 2 | Cold in Place Recycling 5" Depth at 25' wide |  |  | 29350 | Syd | 8.5 | 249475
[5 empty] | HMA Over Aggregate @ 220 psy at 24' wide |  |  | 3100 | Ton | 65 | 201500 | 59.36 | 184016
*Coordination with Mason CRC for adding minimum 3" aggregate on entire roadway. Contractor responsible for initial and final grade shaping.
2P | Victory Twp | Sugar Grove Rd | Stiles Road easterly 2.5 miles toward US-31 | 2.5 | HMA LVSP or 5E1, Wedging Over Aggregate Shoulder at 8' wide and HMA Overlay @ 165#/Syd @ 28' wide (Est. 1,400 ton wedge & 3,420 Overlay) | 0 | 0 | 4820 | Ton | 65 | 313300 | 59.36 | 286115.2 |  | 0 | 0%
[5 empty] | *Optional - Cold-Mill HMA Butt Joints (50' at each end - 1.5" to 0") |  |  | 2 | Each | 1500 | 3000 | 1740 | 3480 |  | 0 | 0%
*Coordination with Mason CRC for grading sod & adding aggregate along shoulder as needed.
3P | Amber/Custer | Scottville Road | Johnson Road N. to US-31 | 0.4 | Cold-Milling HMA 1.5" (millings hauled to MCRC yard - 510 E. State Street, Scottville) | 2020 |  | 7900 | Syd | 2 | 15800 | 1.2 | 9480 |  | 0 | 0%
[5 empty] | *Optional - Cold-Mill HMA Butt Joints (50' at each end - 2." to 0") | 2020 |  | 1 | Each | 1500 | 1500 | 1740 | 1740 |  | 0 | 0%
[5 empty] | HMA LVSP Overlay @ 220 psy at 22' wide | 2020 |  | 870 | Ton | 70 | 60900 | 66.31 | 57689.7 |  | 0 | 0%
4P | Custer | Custer Rd | Chauvez to Hawley | 2 | HMA LVSP Overlay @ 170 #/syd at 22' wide | 2019-08-13 | 2151.92 | 2200 | Ton | 65 | 143000 | 62.9 | 138380 |  | 135355.768 | 97.81%
[5 empty] | *Optional - Cold-Mill HMA Butt Joints (50' at each end - 1.5" to 0") |  | 0 | 2 | Each | 1500 | 3000 | 1740 | 3480 |  | 0 | 0%
5P | Sherman | US-31 (NB) | Fountain Road to Colburn & Townline to Freeman | 2.75 | Cold-Milling HMA 1.5" (millings hauled to MCRC yard - 510 E. State Street, Scottville) | 2019-09-20 | 16561 | 5600 | Syd | 2 | 11200 | 1.24 | 6944 |  | 20535.64 | 295.7%
[5 empty] | HMA 5E3 Overlay @ 170 #/syd | 2019-09-20 | 1380.42 | 476 | Ton | 80 | 38080 | 72.75 | 34629 |  | 100425.555 | 290%
6P | Freesoil | US-31 (SB) | N. of Beyer to Fountain Road | 1.75 | Cold-Milling HMA 1.5" (millings hauled to MCRC yard - 510 E. State Street, Scottville) | 2019-09-21 | 10456 | 6667 | Syd | 2 | 13334 | 1.27 | 8467.09 |  | 13279.12 | 156.8%
[5 empty] | HMA 5E3 Overlay @ 170 #/syd | 2019-09-21 | 906.94 | 566 | Ton | 70 | 39620 | 71.75 | 40610.5 |  | 65072.945 | 160.2%
7P* | Custer | Custer Rd | Conrad to Wilson Road | 1 | HMA 36A Wedge, 8'-9' wide w/LG, at selected locations, both lanes. | 2019-07-22 | 869.86 | 600 | Ton | 70 | 42000 | 69.07 | 41442 |  | 60081.2302 | 145%
8P* | Summit | S. Lakeshore Dr | Consumers Power Bridge N. 600' | 0.12 | HMA 36A Wedge, 12'-13' wide w/LG, both lanes. | 2019-07-08 | 147.64 | 140 | Ton | 100 | 14000 | 90 | 12600 |  | 13287.6 | 105.5%
9P* | Pere Marquette | Rasmussen | Jebavy Drive E. 2,500' | 0.48 | HMA 36A Wedge, 6'-7' wide, at selected locations, both lanes. | 6/27 & 7/8 | 101.96 | 120 | Ton | 100 | 12000 | 93 | 11160 |  | 9482.28 | 84.97%
10P* | Riverton | Hawley Road | 1/4 mile W of Morton E. to Stiles | 1.25 | HMA 36A Wedge, 6'-7' wide, at selected locations, both lanes. | 2019-07-08 | 293.05 | 300 | Ton | 80 | 24000 | 84 | 25200 |  | 24616.2 | 97.68%
11P* | Riverton | Chauvez | 1/4 mile W. of Hogenson to 1/4 mile E. of Hogenson | 0.5 | HMA 36A Wedge, 6'-7' wide, at selected locations, both lanes. | 2019-07-13 | 147.12 | 130 | Ton | 100 | 13000 | 93 | 12090 |  | 13682.16 | 113.2%
12P** | Grant | Townline & Quarterline | Stiles to Quarterline & Townline to Countyline | 7.3 | HMA 36A Wedge, 11.5' wide, at selected locations, both lanes. | 2019-06-26 | 247.39 | 235 | Ton | 80 | 18800 | 90 | 21150 |  | 22265.1 | 105.3%
13P | Summit | Lakeshore Drive | Between Washington & Sunset Lane | 0.12 | HMA LVSP Overlay @ 165 #/syd at 22' wide | 2019-06-28 | 150.19 | 126 | Ton | 100 | 12600 | 95 | 11970 |  | 14268.05 | 119.2%
[7 empty] | 6396.49 | 14393 | Ton | Subtotal | 1062004 | Subtotal | 977736.59 |  | 492351.6482 | 50.36%
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | UNIT | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
[5 empty] | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
[5 empty] | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 150 | 11250 | 140 | 10500
** HMA 36A Wedging SHALL be completed on or before June 15, 2019 |  |  |  |  | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 100 | 15000 | 95 | 14250
* HMA 36A Wedging Projects SHALL be completed on or before August 1, 2019 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 28, 2019 | [9 empty] | Subtotal | 71250 | Subtotal | 70800
UPDATED 11/11/2019
|  |  | 2019 HMA SURFACING - BID SUMMARY PER QUADRANT |  |  |  | Actual | Estimated |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION
[5 empty] | Township Projects by Quadrant: SOUTHWEST (Pere Marquette, Summit and Riverton Townships) | 97.24% | 3728.16 | 3834 | Ton |  | 298165 |  | 270491.9
[5 empty] | Township Projects by Quadrant: SOUTHEAST (Custer, Eden, Logan and Branch Townships) | 105.2% | 1209.29 | 1150 | Ton |  | 103200 |  | 95294.92
[5 empty] | Township Projects by Quadrant: NORTHEAST (Free Soil, Sherman, Sheridan and Meade Townships) | 105.5% | 3050.18 | 2890 | Ton |  | 131650 |  | 123702.7
[5 empty] | Township Projects by Quadrant: NORTHWEST (Hamlin, Amber, Victory and Grant Townships) | 65.34% | 1174.87 | 1798 | Ton |  | 137320 |  | 134116.94
[5 empty] | County Primary Projects | 44.44% | 6396.49 | 14393 | Ton |  | 1062004 |  | 977736.59 | STR#
[10 empty] | TOTAL AMOUNT | 1732339 | TOTAL AMOUNT | 1601343.05 | 3.66
3.79
REVISIONS
2019-03-08
2019-04-22
2019-04-25
2019-05-20
2019-07-15
Anticipated
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 200 |  |  |  | Total Primary | 977736.59 |  | 1077018.1482
[5 empty] | HMA Mix, 51 - 100 Ton |  |  | 150 |  |  |  | MDOT Primary | -207682 |  | -207682
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 100 |  |  |  | MDOT Primary | -247620 |  | -247620
[5 empty] | HMA Mix, 201 - 500 Ton |  |  | 80 |  |  | HMA | MCRC Primary | 522434.59 |  | 621716.1482
[5 empty] | HMA Mix, 501 - 1000 Ton |  |  | 70
[5 empty] | HMA Mix, 1000+ Ton |  |  | 65
2018 | Sherman | Darr Road | Between Sugar Grove & Mavis Road (780' S of HMA & 330' N of HMA) | 0.21 | HMA over aggregate base, 28' wide including lip gutter @ 220#/Syd | 2020 |  | 400 | Ton | 85 | 34000 | 64 | 25600

## 2020 HMA Estimated Quantities (hidden)
2020 HMA SURFACING |  |  |  |  | UPDATED 11/18/2020 ERN
Township Projects by Quadrant: SOUTHWEST (Pere Marquette, Summit and Riverton Townships)
|  |  |  | LENGTH |  |  | Actual | PLAN |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION |  |  | Actual | Actual
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT |  | AMOUNT | Percent
051 | Pere Marquette | Virnetta Drive | Washington Avenue to Rath Avenue (Storm Sewer Install 8-1-2020) | 0.52 | HMA Overlay @ 165 #/syd over entire roadway (21' Wide) | 2020-07-27 | 575.07 | 530 | Ton | 85 | 45050 | 75.18 | 39845.4 |  | 43233.7626 | 108.5% | -1816.2374
|  | Virnetta Drive | HMA Patches |  |  | 2020-07-27 | 40 |  | Ton | 120 | 0 | 117.5 | 0 |  | 4700 |  | 4700
052 | Pere Marquette | Hill Side Road | Jebavy to Cul-de-sac (Riser Rings Required) | 0.55 | HMA Overlay @ 165 #/syd over entire roadway (21' - 26' Wide) | 2020-06-16 | 755.14 | 702 | Ton | 85 | 59670 | 68.5 | 48087 |  | 51727.09 | 107.6% | -7942.91
053 | Pere Marquette | Lake Avenue | M-116 to Beech Avenue (Water Main Work) | 0.06 | HMA Overlay @ 165 #/syd over entire roadway (18' Wide) | 2020-06-13 | 57 | 57 | Ton | 150 | 8550 | 112.05 | 6386.85 |  | 6386.85 | 100% | -2163.15
054 | Pere Marquette | Beech Avenue | Lake Avenue south to end of road (Water Main Work) | 0.16 | HMA Overlay @ 165 #/syd over entire roadway (19' Wide) | 2020-06-13 | 152.95 | 149 | Ton | 110 | 16390 | 80.44 | 11985.56 |  | 12303.298 | 102.7% | -4086.702
055 | Pere Marquette | Terri Court | Juanita to Orchard Avenue (Water Main Work) | 0.06 | HMA Overlay @ 165 #/syd over entire roadway (16' Wide) | 2020-06-13 | 42 | 42 | Ton | 150 | 6300 | 112.05 | 4706.1 |  | 4706.1 | 100% | -1593.9
056 | Pere Marquette | Juanita Avenue | Beech Avenue to end of HMA near lake (Water Main Work) | 0.1 | HMA Overlay @ 165 #/syd over entire roadway (20' Wide) | 2020-06-13 | 123.95 | 120 | Ton | 110 | 13200 | 74.46 | 8935.2 |  | 9229.317 | 103.3% | -3970.683
057 | Pere Marquette | Pleasant Ridge Road | Sherman St to Riverview Drive | 0.35 | HMA Overlay @ 165 #/syd over entire roadway (22' Wide & 2100' lip gutter) | 2020-05-12 | 430 | 430 | Ton | 110 | 47300 | 75.18 | 32327.4 |  | 32327.4 | 100% | -14972.6
058 | Pere Marquette | West Johnson | Jebavy to Cul-de-sac | 0.5 | HMA Overlay @ 165 #/syd over entire roadway (19' Wide include cul-de-sac) | 2020-06-02 | 268.88 | 290 | Ton | 95 | 27550 | 75.18 | 21802.2 |  | 20214.3984 | 92.72% | -7335.6016
059 | Pere Marquette | Curtwood Road | N Lendale to N Sherman | 0.2 | HMA Overlay @ 165 #/syd over entire roadway (20' Wide) | 2020-05-12 | 185.94 | 180 | Ton | 110 | 19800 | 84.81 | 15265.8 |  | 15769.5714 | 103.3% | -4030.4286
160 | Pere Marquette | W Hazelwood Road | S Jebavy to Oakwood | 0.2 | HMA Overlay @ 165 #/syd over entire roadway (19''-20' Wide) | 2020-06-02 | 221.55 | 215 | Ton | 110 | 23650 | 72.59 | 15606.85 |  | 16082.3145 | 103% | -7567.6855 | -50779.8981 | 267460 | 216680.1019
011 | Summit | Park Street | Lakeshore to Cala 740' and the corner of Cala and Lenox 80' Radius | 0.16 | HMA Overlay @ 220 #/syd over entire roadway (20' Wide) | 2020-06-18 | 132.87 | 204 | Ton | 110 | 22440 | 80.44 | 16409.76 |  | 10688.0628 | 65.13% | -11751.9372
015 | Summit | Mack Road | North of North Ave to Turnaround | 0.22 | HMA Wedge @ 165 #/syd at three locations | 2020-06-18 | 35 | 35 | Ton | 200 | 7000 | 190 | 6650 |  | 6650 | 100% | -350 | -12101.9372
[7 empty] | 3020.35 | 2954 | Ton | Subtotal | 296900 | Subtotal | 228008.12 |  | 234018.1647 | 102.6%
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | UNIT | UNIT PRICE | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 150 | 11250 | 140 | 10500
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 100 | 15000 | 95 | 14250
** HMA 36A Wedging SHALL be completed on or before June 1, 2020 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 30, 2020 | [9 empty] | Subtotal | 71250 | Subtotal | 70800
2020 HMA SURFACING (Continued) |  |  |  |  | UPDATED 11/18/2020 ERN
Township Projects by Quadrant: SOUTHEAST (Custer, Eden, Logan and Branch Townships)
|  |  |  | LENGTH |  |  | Actual | PLAN |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION |  |  | Actual | Actual
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT |  | AMOUNT | Percent
081 | Branch | Barothy Road | Starting 525' East of Barothy lodge continure west 6,129' to Whalhalla Rd | 1.2 | HMA 36A Overlay @ 110 #/syd over entire roadway (22' Wide) | CANCELED |  | 830 | Ton | 85 | 70550 | 77.81 | 64582.3 |  | 0 | 0%
083 | Branch | Weaver Road | US-10 east to Campbell Rd | 0.6 | HMA 36A Wedge full lane north side | 2020-06-29 | 271.94 | 300 | Ton | 95 | 28500 | 85.61 | 25683 |  | 23280.7834 | 90.65% | -5219.2166
* MCRC will need to add Aggregate to the shoulder prior to paving
085 | Branch | Weaver Road | US-10 east to Campbell Rd | 0.6 | HMA 36A Wedge full lane south side | 2020-10-13 | 219.83 | 205 | Ton | 90 | 18450 | 85.61 | 17550.05 |  | 18819.6463 | 107.2%
084 | Branch | Shoshone Trail & Chickasaw | Chickasaw to Navago & Shoshone | 0.6 | HMA Wedge at select locations | 2020-10-15 | 247.14 | 205 | Ton | 90 | 18450 | 85.61 | 17550.05 |  | 21157.6554 | 120.6%
072 | Custer | Wilson Road | From Stephens Road continuing east for 650' both sides of Road |  | HMA 36A or 5E1 full width Wedging | 2020-09-01 | 111 | 105 | Ton |  |  | 95 | 9975 |  | 10545 | 105.7%
071 | Custer | Conrad Road | 525' east of Darr and 177' east of Tuttle | 0.13 | HMA Wedge at select locations | 2020-09-01 | 63.95 | 61 | Ton | 160 | 9760 | 135 | 8235 |  | 8633.25 | 104.8%
[7 empty] | 913.86 | 876 | Ton | Subtotal | 99050 | Subtotal | 78993.1 |  | 82436.3351 | 104.4%
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | UNIT | UNIT PRICE | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 150 | 11250 | 140 | 10500
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 100 | 15000 | 95 | 14250
** HMA 36A Wedging SHALL be completed on or before June 1, 2020 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 30, 2020 | [9 empty] | Subtotal | 71250 | Subtotal | 70800
2020 HMA SURFACING (Continued) |  |  |  |  | UPDATED 11/18/2020 ERN
Township Projects by Quadrant: NORTHEAST (Free Soil, Sherman, Sheridan and Meade Townships)
|  |  |  | LENGTH |  |  | Actual | PLAN |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION |  |  | Actual | Actual
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT |  | AMOUNT | Percent
2018 | Sherman | Darr Road | Between Sugar Grove & Mavis Road (780' S of HMA & 330' N of HMA) | 0.21 | HMA over aggregate base, 28' wide including lip gutter @ 220#/Syd | 2020-06-05 | 410.51 | 400 | Ton | 85 | 34000 | 64 | 25600 |  | 26272.64 | 102.6%
141 | Freesoil | Reek, Ottawa, MeeNAhGa | Starting oat the hill on Reek continuing around to the top of hill on Ottawa and then south on Mee Nah Ga Lane |  | Overlay @ 2" with valley gutter (MCRC needs to add 4" of gravel prior to HMA) | POSTPONED |  | 428 | Ton | 95 | 40660 | 80 | 34240 |  | 0 | 0%
[5 empty] | Property Owner in low spot did not want any road water on his property. |  |  |  | Ton | 65 | 0 | 64.69 | 0 |  | 0 | #DIV/0!
| Sheridan | Fountain Road | Starting at Benson Road westerly to Larson Road | 1.4 | LVSP Overlay @ 165#/Syd (7,271' x 21.5') (MCRC needs to install a culvert) | 2020-10-28 | 1481.05 | 1450 | Ton | 75 | 108750 | 64.96 | 94192 |  | 96209.008 | 102.1%
| Sheridan | Benson Road | Millerton Road north to Ford Lake | 0.5 | LVSP Overlay @ 165#/Syd (2,677' x 22') | 2020-10-30 | 438.41 | 540 | Ton | 85 | 45900 | 64.96 | 35078.4 |  | 28479.1136 | 81.19%
[7 empty] | 2329.97 | 2390 | Ton | Subtotal | 229310 | Subtotal | 154870.4 |  | 150960.7616 | 97.48%
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | UNIT | UNIT PRICE | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 150 | 11250 | 140 | 10500
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 100 | 15000 | 95 | 14250
** HMA 36A Wedging SHALL be completed on or before June 1, 2020 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 30, 2020 | [9 empty] | Subtotal | 71250 | Subtotal | 70800
2020 HMA SURFACING (Continued) |  |  |  |  | UPDATED 11/18/2020 ERN
Township Projects by Quadrant: NORTHWEST (Hamlin, Amber, Victory and Grant Townships)
|  |  |  | LENGTH |  |  | Actual | PLAN |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION |  |  | Actual | Actual
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT |  | AMOUNT | Percent
062 | Amber | Conrad | Victory Corner east to wedging last year |  | Apply Wedging in selected arears | 2020-06-18 | 92.53 | 91 | Ton | 67.97 | 6185.27 | 67.97 | 6185.27 |  | 6289.2641 | 101.7% | 103.9941
065 | Amber | Dennis Road | Starting 1358' North of Hansen & continuing 732' |  | HMA LVSP over Aggregate @ 240#/syd at 28' wide with LG | 2020-09-21 | 300.04 | 315 | Ton |  |  | 74.19 | 23369.85 |  | 22259.9676 | 95.25%
066 | Amber | First Street | Brye to Stiles | 1.93 | HMA LVSP over Aggregate @ 240#/syd at 22' wide | 9/24/2020 & 9/25/2020 | 3088.89 | 2980 | Ton |  |  | 60.07 | 179008.6 |  | 185549.6223 | 103.7%
*098 | Hamllin | Beaune | Angling north |  | Apply Wedging in selected arears | 2020-06-24 | 31.18 | 31 | Ton | 200 | 6200 | 190 | 5890 |  | 5924.2 | 100.6% | -275.8
*** MCRC needs to uncut & remove clay, add gravel prior to HMA
099B | Hamlin | Rath Road | Jagger Road north 800' | 0.15 | HMA LVSP Over Aggregate @ 220 psy at 22' wide | 6/15/2020 & 7/2/2020 | 265.01 | 216 | Ton | 95 | 20520 | 90 | 19440 |  | 23850.9 | 122.7% | 3330.9
094 | Hamlin | Piney Ridge Road | M-116 continuing north | 1.5 | HMA 36A Wedge, 6'-7' wide, at selected locations, 1,900' east lane & 2,000' west lane. | 2020-07-06 | 241.29 | 220 | Ton | 95 | 20900 | 84 | 18480 |  | 20268.36 | 109.7% | -631.64 | -907.44
135 | Grant | LaSalle | Between Hoague Road & US-31 (Misc. spot overlays) |  | HMA LVSP Over Aggregate @ 165 psy at 22' wide | 2020-06-24 | 106.39 | 124 | Ton | 95 | 11780 | 95 | 11780 |  | 10107.05 | 85.8% | -1672.95
132 | Grant | Morton Road | Countyline Road south to Sass Road | 0.5 | HMA 36A Wedge, 6'-7' wide, at selected locations. | 2020-06-29 | 244.7 | 260 | Ton | 90 | 23400 | 90 | 23400 |  | 22023 | 94.12% | -1377 | -3049.95
| Grant | Countyline Road | Quarterline west 9,437' to end of HMA |  | HMA 5E1/36A Wedge 11' x 0 @ CL & 1.5" @ 11' - Select Locations |  |  | 336 | Ton
[7 empty] | 4370.03 | 4573 | Ton | Subtotal | 88985.27 | Subtotal | 287553.72 |  | 296272.364 | 103%
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | UNIT | UNIT PRICE | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 150 | 11250 | 140 | 10500
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 100 | 15000 | 95 | 14250
** HMA 36A Wedging SHALL be completed on or before June 1, 2020 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 80 | 20000 | 90 | 22500
* HMA Overlay Projects SHALL be completed on or before September 30, 2020 | [9 empty] | Subtotal | 71250 | Subtotal | 70800
UPDATED 11/18/2020 ERN
County Primary Projects |  |  |  | LENGTH |  |  | Actual | PLAN |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION |  |  | Actual | Actual
JOB # | TOWNSHIP | ROAD NAME | TERMINI | LENGTH (mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT |  | AMOUNT | Percent
1P | Sherman | Sugar Grove Rd | US-31 to Tuttle Road | 2 | HMA LVSP or 5E1, Wedging Over Aggregate Shoulder at 8' wide and HMA Overlay @ 165#/Syd @ 26' wide (Est. 1,100 ton wedge & 2,710 Overlay) | 10/5/2020 & 10/7/2020 & 10/8/2020 | 4534 | 3810 | Ton | 65 | 247650 | 59.36 | 226161.6 |  | 269138.24 | 119%
|  |  | Actual totals Wedging with ski @ 2% 2450 tons & 2084 tons @ 125# Surface |  |  |  |  | 1 | Each | 1500 | 1500 | 1740 | 1740 |  | 0 | 0%
3P | Amber/Custer | Scottville Road | Johnson Road N. to US-31 | 0.4 | Cold-Milling HMA 1.5" (millings hauled to MCRC yard - 510 E. State Street, Scottville) | 2020-06-05 | 5070 | 7900 | Syd | 2 | 15800 | 1.2 | 9480 |  | 6084 | 64.18%
[5 empty] | *Optional - Cold-Mill HMA Butt Joints (50' at each end - 2." to 0") |  | 0 | 1 | Each | 1500 | 1500 | 1740 | 1740 |  | 0 | 0%
[5 empty] | HMA LVSP Overlay @ 220 psy at 22' wide | 2020-06-05 | 801.09 | 870 | Ton | 70 | 60900 | 66.31 | 57689.7 |  | 53120.2779 | 92.08%
4P | Riverton & Summit | PM Highway | US-31 to South County Line | 6.7 | HMA Wedging various locations as marked | 2020-06-17 | 228.5 | 210 | Ton | 90 | 18900 | 90 | 18900 |  | 20565 | 108.8%
5P | Victory | Fountain Road | Stiles & Angling westerly to Jebavy Drive | 4.7 | HMA Overlay @ 120# Jebavy to Beaune Road then 145# @ 28' wide | 9/11/2020 & 9/17/20 & 9/18/20 &9/21/20 | 5557.23 | 5600 | Ton | 65 | 364000 | 61.77 | 345912 |  | 343270.0971 | 99.24%
[5 empty] | HMA Wedging various locations as marked | 9/11/2020 & 9/8/20 | 153.6 | 150 | Ton | 65 | 9750 | 61.77 | 9265.5 |  | 9487.872 | 102.4%
6P | Riverton | Scottville Road | Chauvez to Washington | 6 | HMA Wedging various locations as marked | 9/2/2020 & 9/3/2020 | 935.24 | 900 | Tons |  |  | 77.53 | 69777 |  | 72509.1572 | 103.9%
| Riverton | Scottville Road | Chauvez to Washington | 6 | HMA Wedging various locations as marked | 2020-09-24 | 90.77 | 150 | Tons |  |  | 77.53 | 11629.5 |  | 7037.3981 | 60.51%
7P | Riverton | Hawley Road | Stiles to Scottville | 3 | HMA Wedging various locations as marked | 2020-09-03 | 897.78 | 700 | Tons |  |  | 77.53 | 54271 |  | 69604.8834 | 128.3% | After Stiles mistake on 8-31-2020
8P | Riverton | Marrision Road | Stiles to Scottville | 3 | HMA Wedging various locations as marked | 8/31/2020 & 9/2/2020 | 455 | 650 | Tons |  |  | 77.53 | 50394.5 |  | 35276.15 | 70%
9P | Riverton | Stiles Road | Marrision to Washington | 1 | HMA Wedging various locations as marked | 2020-08-31 | 770 | 900 | Tons |  |  | 77.53 | 69777 |  | 59698.1 | 85.56%
| Riverton | Stiles Road | Marrision to Washington | 1 | HMA Wedging 8' wide 0" to ?" (run slope @ 2% ideal to 3% max.) | 2020-09-24 | 350 | 250 | Tons |  |  | 77.53 | 19382.5 |  | 27135.5 | 124.4% | After Board Meeting on 9-10-2020
MDOT TWA | Scottville | US-10 | Main St to High St | 0.5 | Mill and Fill various locations as marked | 2020-09-01 | 326.43 | 300 | Tons |  |  |  | 140 |  | 0 | 0%
[7 empty] | 14682.44 | 14490 | Ton | Subtotal | 691450 | Subtotal | 946120.3 |  | 972926.6757 | 102.8%
** HMA 36A Wedging SHALL be completed on or before June 1, 2020
* HMA Overlay Projects SHALL be completed on or before September 30, 2020 |  |  |  |  | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | UNIT | UNIT | UNIT PRICE | AMOUNT | UNIT PRICE | AMOUNT
[5 empty] | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 2.5 | 8750 | 2.05 | 7175
[5 empty] | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 1.5 | 11250 | 1.55 | 11625
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 200 | 5000 | 190 | 4750
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 150 | 11250 | 140 | 10500
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 100 | 15000 | 95 | 14250
[5 empty] | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 80 | 20000 | 90 | 22500
[10 empty] | Subtotal | 71250 | Subtotal | 70800
UPDATED 11/18/2020 ERN
|  |  | 2020 HMA SURFACING - BID SUMMARY PER QUADRANT |  |  |  | Actual | Estimated |  | ENGINEER'S ESTIMATE |  | RIETH-RILEY CONSTRUCTION
|  | New to 2020 | Township Projects by Quadrant: SOUTHWEST (Pere Marquette, Summit and Riverton Townships) |  |  | 102.2% | 3020.35 | 2954 | Ton |  | 296900 |  | 228008.12
|  | Carry Over | Township Projects by Quadrant: SOUTHWEST (Pere Marquette, Summit and Riverton Townships) | [5 empty] | Ton
|  | New to 2020 | Township Projects by Quadrant: SOUTHEAST (Custer, Eden, Logan and Branch Townships) |  |  | 104.3% | 913.86 | 876 | Ton |  | 99050 |  | 78993.1
|  | Carry Over | Township Projects by Quadrant: SOUTHEAST (Custer, Eden, Logan and Branch Townships)
|  | New to 2020 | Township Projects by Quadrant: NORTHEAST (Free Soil, Sherman, Sheridan and Meade Townships)
|  | Carry Over | Township Projects by Quadrant: NORTHEAST (Free Soil, Sherman, Sheridan and Meade Townships) |  |  | 97.49% | 2329.97 | 2390 | Ton |  | 229310 |  | 154870.4
|  | New to 2020 | Township Projects by Quadrant: NORTHWEST (Hamlin, Amber, Victory and Grant Townships) |  |  | 95.56% | 4370.03 | 4573 | Ton |  | 88985.27 |  | 287553.72
|  | Carry Over | Township Projects by Quadrant: NORTHWEST (Hamlin, Amber, Victory and Grant Townships)
|  | New to 2020 |  |  | County Primary Projects
|  | Carry Over |  |  | County Primary Projects | 101.3% | 14682.44 | 14490 | Ton |  | 691450 |  | 946120.3 | STR#
[5 empty] | 27642.65 |  | 25316.65 | 25283 | Ton | TOTAL AMOUNT | 1405695.27 | TOTAL AMOUNT | 1695545.64 | 3.66
[13 empty] | 120.6% | 3.79

## 2022 HMA Bidding Sheet XLS
2022 HMA SURFACING
Township Projects by Quadrant: SOUTHWEST (Pere Marquette, Summit and Riverton Townships)
|  |  |  | LENGTH |  |  | Actual | PLAN |  | CONTRACTOR
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (ft or mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT
051 | Pere Marquette | S. Lakeshore Drive | Buttersville Park to Top of the Hill, 600' | 0.11 | HMA Paving @ 330 #/syd (2 lifts) over entire roadway (26' Wide + LG E. Side') |  |  | 310 | Ton | 0 | 0
MCRC to undercut, place geogrid, aggregate prior to HMA
052 | Pere Marquette | Bradshaw Road | Inman to Brunson, 3,931' | 0.75 | HMA Overlay @ 220 #/syd over entire roadway (20 -22' Wide) |  |  | 961 | Ton | 0 | 0
053 | Pere Marquette | Patterson Road | Lakeshore westerly, 760' | 0.14 | HMA Overlay @ 165 #/syd over entire roadway (20 -22' Wide) |  |  | 140 | Ton | 0 | 0
054 | Pere Marquette | Speer Road | S. of Patterson, 726' Including cul-de-sac | 0.14 | 275' HMA Wedging & HMA Overlay @ 165 #/syd over entire roadway (20 -22' Wide) |  |  | 220 | Ton | 0 | 0
055 | Pere Marquette | Dunecrest Ave. | S. Lakeshore Drive to S. Shoreview, 950' | 0.18 | HMA Overlay @ 165 #/syd over entire roadway (20 -22' Wide) |  |  | 186 | Ton | 0 | 0
056 | Pere Marquette | Shoreview Court | Shoreview Court including two (2) cul-de-sacs | 0.07 | HMA Overlay @ 165 #/syd over entire roadway (20 -22' Wide) |  |  | 248 | Ton | 0 | 0
057 | Pere Marquette | Riverview Drive | Pleasant Ridge Road to Pleasant Ridge Road | 0.35 | HMA Overlay @ 165 #/syd over entire roadway (20 -22' Wide) |  |  | 373 | Ton | 0 | 0
058 | Pere Marquette | Pleasant Ridge | W. Riverview to W. Riverview | 0.13 | HMA Overlay @ 165 #/syd over entire roadway (20 -22' Wide) |  |  | 158 | Ton | 0 | 0
011 | Riverton/Summit | Brye Road | Hawley to Anthony 10,438' | 1.98 | Select wedging 10' to 11' Wide - Prior to Chip Seal |  |  | 261 | Ton | 0 | 0
012 | Summit | G Street | Lakeshore Drive west for 300' | 0.06 | HMA Paving @ 240 #/syd over entire roadway (16' Wide + LG S. Side') |  |  | 75 | Ton | 0 | 0
MCRC to prepare gravel base prior to HMA
013 | Summit | Mack Road | North Ave to Thiele Road (950') | 0.018 | Select wedging 10' to 11' Wide - Prior to Chip Seal |  |  | 55 | Ton | 0 | 0
014 | Summit | Brunson Road | Deren to Meisenheimer 2,290' | 0.43 | Select wedging 10' to 11' Wide - Prior to Chip Seal |  |  | 45 | Ton | 0 | 0
[7 empty] | 0 | 3032 | Ton | Subtotal | 0
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | QTY | UNIT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 0 | 0
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 0 | 0
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 0 | 0
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 0 | 0
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 0 | 0
** HMA Wedging SHALL be completed on or before July 1, 2022 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 0 | 0
* HMA Overlay Projects SHALL be completed on or before October 28, 2022 | [9 empty] | Subtotal | 0
2022 HMA SURFACING (Continued)
Township Projects by Quadrant: SOUTHEAST (Custer, Eden, Logan and Branch Townships)
|  |  |  | LENGTH |  |  | Actual | PLAN |  | CONTRACTORS
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (ft or mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT
081 | Branch | Taylor Road | Walhalla Shores N. to Filburn, 1,850' | 0.35 | HMA Paving over Aggregate @ 240 #/syd over entire roadway (22' Wide) |  |  | 550 | Ton | 0 | 0
MCRC to remove HMA, undercut, aggrgate prior to HMA
041 | Logan | Anthony Road | Anthony Road from Masten Road to Woods Road, 3,694' | 0.7 | HMA Paving over Aggregate @ 240 #/syd over entire roadway (22' to 26' wide w/LG) |  |  | 1360 | Ton | 0 | 0
MCRC to do earthwork, undercutting, culverts, aggregate base prior to HMA
xxx | Custer
xxx | Eden
[7 empty] | 0 | 1910 | Ton | Subtotal | 0
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | QTY | UNIT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 0 | 0
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 0 | 0
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 0 | 0
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 0 | 0
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 0 | 0
** HMA Wedging SHALL be completed on or before July 1, 2022 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 0 | 0
* HMA Overlay Projects SHALL be completed on or before October 28, 2022 | [9 empty] | Subtotal | 0
2022 HMA SURFACING (Continued)
Township Projects by Quadrant: NORTHEAST (Free Soil, Sherman, Sheridan and Meade Townships)
|  |  |  | LENGTH |  |  | Actual | PLAN |  | CONTRACTOR
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (ft or mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT
143 | Freesoil | Reek, Ottawa & Mee Nah Ga Lane | Starting at the hill on Reek continuing S & E to the top of the hill on Ottawa. South on Mee Nah Ga to the end, 1,450' | 0.27 | HMA Paving over Aggregate @ 240 #/syd over entire roadway (22' to 26' wide w/LG) |  |  | 428 | Ton | 0 | 0
MCRC to install storm sewer, aggregate base prior to HMA
121 | Sheridan | East Ford Lake Road | from 200' West of Griffin for 390' | 0.07 | HMA Paving over Aggregate @ 240 #/syd over entire roadway (26' wide w/LG) |  |  | 175 | Ton | 0 | 0
MCRC to add aggregate, grade & compact gravel base prior to HMA
122 | Sheridan | Mustang Road | Fountain Road N. 415' | 0.08 | HMA Paving over Aggregate @ 240 #/syd over entire roadway (26' wide w/LG) |  |  | 180 | Ton | 0 | 0
MCRC to add aggregate, grade & compact gravel base prior to HMA
123 | Sheridan | Hughes Road | Fountain Road N. 460' | 0.09 | HMA Paving over Aggregate @ 240 #/syd over entire roadway (26' wide w/LG) |  |  | 195 | Ton | 0 | 0
MCRC to add aggregate, grade & compact gravel base prior to HMA
152 | Mead | Budzinski Road | Freesoil Road to Bennett Road, 2,600' | 0.49 | Select wedging 10' to 11' |  |  | 97 | Ton | 0 | 0
[7 empty] | 0 | 1075 | Ton | Subtotal | 0
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | QTY | UNIT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 0 | 0
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 0 | 0
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 0 | 0
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 0 | 0
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 0 | 0
** HMA Wedging SHALL be completed on or before July 1, 2022 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 0 | 0
* HMA Overlay Projects SHALL be completed on or before October 28, 2022 | [9 empty] | Subtotal | 0
2022 HMA SURFACING (Continued)
Township Projects by Quadrant: NORTHWEST (Hamlin, Amber, Victory and Grant Townships)
|  |  |  | LENGTH |  |  | Actual | PLAN |  | CONTRACTOR
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (ft or mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT
xxx | Amber
xxx | Grant
160 | Hamlin | Larch Drive & Larchwood | Piney Ridge east 1,314' & Larchwood north 620' | 0.37 | HMA Paving over Aggregate @ 240 #/syd over entire roadway (20' to 22' wide) |  |  | 570 | Ton | 0 | 0
MCRC to add aggregate, grade & compact gravel base prior to HMA
163 | Hamlin | Piney Ridge | Various Segments north of Larch between 3264 & 3130 | 640' | HMA wedging and HMA Overlay 19' wide @ 120#/syd |  |  | 160 | Ton | 0 | 0
102 | Victory | Victory Corner Road | starting at 105' north of Dewey south to 1,150' | 0.22 | Select wedging 10' to 11' Wide - Prior to Chip Seal |  |  | 75 | Ton | 0 | 0
104 | Victory | Dewey Road | Stiles to Amber, 5,164' | 0.98 | Select wedging 10' to 11' Wide - Prior to Chip Seal |  |  | 205 | Ton | 0 | 0
[7 empty] | 0 | 1010 | Ton | Subtotal | 0
XXX | Contracts not received by MCRC - Pending Township Approval
[5 empty] | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | QTY | UNIT | UNIT PRICE | AMOUNT
| Note: Twp Jobs to be awarded per quadrant as a whole. |  |  |  | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 0 | 0
| Unnumber Jobs are contingent upon Township approval. |  |  |  | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 0 | 0
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 0 | 0
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 0 | 0
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 0 | 0
** HMA Wedging SHALL be completed on or before July 1, 2022 |  |  |  |  | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 0 | 0
* HMA Overlay Projects SHALL be completed on or before October 28, 2022 | [9 empty] | Subtotal | 0
2022 HMA SURFACING (Continued)
County Primary Projects |  |  |  | LENGTH |  |  | Actual | PLAN |  | CONTRACTOR
JOB # | TOWNSHIP | ROAD NAME | TERMINI | (ft or mi) | ACTIVITY | Date | Qty | QTY | UNIT | UNIT PRICE | AMOUNT
1P | Riverton | Chauvez Road | Stiles to Scottville Road (2,800' x 10' x 100#) | 3 | Select wedging various locations 5' to 11' Wide - Prior to Chip Seal |  |  | 200 | Ton | 0 | 0
2P | Riverton | Stiles Road | Chauvez to Marrison Road (19,500' x 10' x 100#) | 5 | Select wedging various locations 5' to 11' Wide - Prior to Chip Seal |  |  | 1100 | Tons | 0 | 0
(Chauvez to Meisenheimer 1,500' x 10' x 100#) (1,250' S. of Meisenheimer to Marrision 18,000' x 10' x 100#)
3P | Pere Marquette | Bryant Road | Sherman to New HMA at Elementary School, 1,360' | 0.26 | HMA Overlay @ 145 #/syd over entire roadway (30' Wide) |  |  | 350 | Tons | 0 | 0
[5 empty] | HMA Butt Joints |  |  | 2 | Each | 0 | 0
4P | Pere Marquette | Jebavy Drive | 2,450' N. of Fisher Road South to Decker Road, 5,150' | 0.98 | HMA Overlay @ 130 #/syd over entire roadway (28' Wide) |  |  | 1050 | Tons | 0 | 0
|  | The length of Jebavy Drive will be adjusted based on available funding. |  |  | HMA Butt Joints |  |  | 2 | Each | 0 | 0
5P | Custer | Custer Road | Wilson Road to Chauvez Road | 1 | HMA Overlay @ 165 #/syd over entire roadway (22' Wide) |  |  | 1150 | Tons | 0 | 0
[5 empty] | HMA Butt Joints |  |  | 2 | Each | 0 | 0
[7 empty] | 0 | 3850 | Ton | Subtotal | 0
** HMA Wedging SHALL be completed on or before July 1, 2022
* HMA Overlay Projects SHALL be completed on or before October 28, 2022 |  |  |  |  | ACTIVITY / TONNAGE - NORTHWEST QUAD. |  |  | QTY | UNIT | UNIT PRICE | AMOUNT
[5 empty] | HMA Base Crushing and Shaping 2,500 to 5,000 |  |  | 3500 | SYD | 0 | 0
[5 empty] | HMA Base Crushing and Shaping 5,000 to 10,000 |  |  | 7500 | SYD | 0 | 0
[5 empty] | HMA Mix, 0 - 50 Ton |  |  | 25 | Ton | 0 | 0
|  |  | Note: Pricing my be considered for award |  | HMA Mix, 51 - 100 Ton |  |  | 75 | Ton | 0 | 0
[5 empty] | HMA Mix, 101 - 200 Ton |  |  | 150 | Ton | 0 | 0
[5 empty] | HMA Mix, 201 Ton and Greater |  |  | 250 | Ton | 0 | 0
[10 empty] | Subtotal | 0
|  |  | 2022 HMA SURFACING - BID SUMMARY PER QUADRANT |  |  |  | Actual | Estimated | Unit | CONTRACTOR
|  | 2022 | Township Projects by Quadrant: SOUTHWEST (Pere Marquette, Summit and Riverton Townships) |  |  |  | 0 | 3032 | Ton |  | 0
|  | 2022 | Township Projects by Quadrant: SOUTHEAST (Custer, Eden, Logan and Branch Townships) |  |  |  | 0 | 1910 | Ton |  | 0
|  | 2022 | Township Projects by Quadrant: NORTHEAST (Free Soil, Sherman, Sheridan and Meade Townships) |  |  |  |  | 1075 | Ton |  | 0
|  | 2022 | Township Projects by Quadrant: NORTHWEST (Hamlin, Amber, Victory and Grant Townships) |  |  |  | 0 | 1010 | Ton |  | 0
|  | 2022 | County Primary Projects |  |  |  | 0 | 3850 | Ton |  | 0
[7 empty] | 0 | 10877 | Ton | TOTAL AMOUNT | 0